## worklogs
Worklog id | Author | Summary | Work description | Issue | Parent | Epic | Project | Started | Assignee | Labels | Priority | Resolution | Reporter | Status | Issue type | Sprint | Time spent
10258 | Morta Marija Matelyte | Metadata deletion from image before saving | Splitting work for each team member for image scoring algorithm development, (all team) writing methods for metadata stripping (individual work), finishing up SE presentation. | GRAF-67 | GRAF-63 | _ | graffinity | Dec 19, 2022, 1:00 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Sub-task | _ | 8h
10253 | Kernius Survila | Fix initial backend tests | uzkniso to 24 min, ilgiau testus rasiau bet, tarkim | GRAF-55 | _ | _ | graffinity | Dec 13, 2022, 5:49 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 6m
10227 | Kernius Survila | NestJS file upload handling |  | GRAF-53 | _ | _ | graffinity | Nov 29, 2022, 8:40 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10228 | Kernius Survila | NestJS file upload handling |  | GRAF-53 | _ | _ | graffinity | Nov 28, 2022, 8:40 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10229 | Kernius Survila | NestJS file upload handling |  | GRAF-53 | _ | _ | graffinity | Nov 24, 2022, 8:41 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10232 | Kernius Survila | NestJS file upload handling | somehing something | GRAF-53 | _ | _ | graffinity | Nov 26, 2022, 8:41 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10217 | Morta Marija Matelyte | Graffitis near me | Researched for algorithms, found the NNS (Nearest Neighbor Search) algorithm, that might work for our project. Also found a package for geolocation in npm. Created a branch and started trying to implement both. Wrote down some questions for the next meeting, that occured to me while researching algorithms for this branch. | GRAF-50 | _ | _ | graffinity | Nov 28, 2022, 7:00 PM | Morta Marija Matelyte | _ | High | _ | Kernius Survila | Backlog | Task | _ | 1h 30m
10265 | Morta Marija Matelyte | Graffitis near me | Taking graffiti photos. | GRAF-50 | _ | _ | graffinity | Jan 8, 2023, 1:00 PM | Morta Marija Matelyte | _ | High | _ | Kernius Survila | Backlog | Task | _ | 1h
10266 | Morta Marija Matelyte | Graffitis near me | Taking graffiti photos and uploading them to google drive. | GRAF-50 | _ | _ | graffinity | Jan 10, 2023, 1:30 PM | Morta Marija Matelyte | _ | High | _ | Kernius Survila | Backlog | Task | _ | 1h
10240 | Dominykas Švilpa | Best picture determination / picture points | ndjasnjdas | GRAF-49 | _ | _ | graffinity | Nov 25, 2022, 6:10 PM | Dominykas Švilpa | _ | High | Done | Kernius Survila | Done | Task | _ | 6h
10155 | Kernius Survila | Learning log | Creating tasks for version 0.2.0 | GRAF-45 | _ | _ | graffinity | Nov 2, 2022, 12:03 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10177 | Dominykas Švilpa | Update Email Functionality | Updating the CRUD opartions on Email functionality | GRAF-39 | GRAF-42 | GRAF-42 | graffinity | Nov 3, 2022, 8:00 PM | Dominykas Švilpa | Backend | High | Done | Kernius Survila | Done | Task | _ | 2h
10260 | Morta Marija Matelyte | Liked Posts Functionality (research & assessment) | Finished like functionality and opened a pull request, wrote some unit tests, but they are not fully functioning. | GRAF-36 | GRAF-42 | GRAF-42 | graffinity | Dec 30, 2022, 11:00 AM | Morta Marija Matelyte | Backend,Research | Low | Done | Kernius Survila | Done | Task | _ | 8h
10179 | Dominykas Švilpa | Update Email Template Functionality | Updating the CRUD opartions on Email Template component | GRAF-35 | GRAF-42 | GRAF-42 | graffinity | Nov 3, 2022, 12:00 PM | Dominykas Švilpa | Backend | High | Done | Kernius Survila | Done | Task | _ | 2h
10210 | Morta Marija Matelyte | Graffiti Functionality, Pop-up Component & Other Updates | Reviewed GRAF-32 pull request, left a comment. | GRAF-32 | GRAF-42 | GRAF-42 | graffinity | Nov 21, 2022, 3:30 PM | Kernius Survila | Backend,Frontend | High | Done | Kernius Survila | Done | Task | _ | 45m
10176 | Dominykas Švilpa | Front-end: developing the drawer section on mobile version | Developing mobile version of the website and preparing it for demonstration | GRAF-31 | GRAF-42 | GRAF-42 | graffinity | Nov 2, 2022, 2:19 PM | Dominykas Švilpa | Frontend | Low | Done | Dominykas Švilpa | Done | Task | _ | 6h
10150 | Kernius Survila | Frontend Graffiti Post Pop Up Component | frontend dev for demo | GRAF-30 | _ | _ | graffinity | Oct 29, 2022, 12:53 PM | Kernius Survila | Frontend | Medium | Done | Kernius Survila | Done | Task | _ | 6h
10138 | Dominykas Švilpa | Developing the front-end | Building the footer element of the Landing page | GRAF-28 | _ | _ | graffinity | Oct 24, 2022, 5:00 AM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 3h
10139 | Dominykas Švilpa | Developing the front-end | Remodeling of the website | GRAF-28 | _ | _ | graffinity | Oct 25, 2022, 1:11 PM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 5h
10143 | Dominykas Švilpa | Developing the front-end | Continue to remodel the website | GRAF-28 | _ | _ | graffinity | Oct 27, 2022, 2:24 PM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 4h
10144 | Dominykas Švilpa | Developing the front-end | Fixing issues with remodeled website | GRAF-28 | _ | _ | graffinity | Oct 29, 2022, 3:30 AM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 4h
10145 | Dominykas Švilpa | Developing the front-end | Remodeling the mobile version of the landing page: moving the header (navigation bar) to the bottom and adjusting border radius | GRAF-28 | _ | _ | graffinity | Oct 30, 2022, 2:27 PM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 2h
10146 | Dominykas Švilpa | Developing the front-end | Creating a drawer for the mobile version that can slide out of the bottom | GRAF-28 | _ | _ | graffinity | Oct 31, 2022, 11:00 AM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 3h
10181 | Dominykas Švilpa | Developing the front-end | Rebuilding the Map Component and adding functionility to the map | GRAF-28 | _ | _ | graffinity | Nov 7, 2022, 9:30 AM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 8h
10182 | Dominykas Švilpa | Developing the front-end | Building map fucntionality that pans to your location | GRAF-28 | _ | _ | graffinity | Nov 8, 2022, 8:00 AM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 5h
10184 | Dominykas Švilpa | Developing the front-end | Making the map responsive to many screens | GRAF-28 | _ | _ | graffinity | Nov 12, 2022, 12:44 PM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 3h
10197 | Dominykas Švilpa | Developing the front-end | Re-rebuilding the map for better functionality load times | GRAF-28 | _ | _ | graffinity | Nov 15, 2022, 2:00 PM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 6h
10198 | Dominykas Švilpa | Developing the front-end | Re-rebuilding the map for better functionality load times | GRAF-28 | _ | _ | graffinity | Nov 16, 2022, 2:00 PM | Dominykas Švilpa | _ | Medium | Done | Dominykas Švilpa | Done | Task | _ | 4h
10149 | Kernius Survila | Graffiti Photo Functionality (research & assessment) | entity & other updates | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Oct 31, 2022, 12:52 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 4h
10162 | Zivile Nebutovaite | Graffiti Photo Functionality (research & assessment) |  | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Nov 6, 2022, 5:17 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 5h
10212 | Zivile Nebutovaite | Graffiti Photo Functionality (research & assessment) | Entity updates and reasearch | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Nov 20, 2022, 8:12 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 5h
10221 | Zivile Nebutovaite | Graffiti Photo Functionality (research & assessment) | Finishinh up Graffiti photo entity functionality | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Nov 28, 2022, 8:09 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 1h 30m
10224 | Zivile Nebutovaite | Graffiti Photo Functionality (research & assessment) | finishing up report entity | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Nov 27, 2022, 8:12 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 2h
10225 | Zivile Nebutovaite | Graffiti Photo Functionality (research & assessment) | Made changes based on comments on pull requests | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Nov 24, 2022, 8:14 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 2h
10230 | Kernius Survila | Graffiti Photo Functionality (research & assessment) |  | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Nov 25, 2022, 8:41 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 4h
10247 | Kernius Survila | Graffiti Photo Functionality (research & assessment) | amazon s3 | GRAF-27 | GRAF-42 | GRAF-42 | graffinity | Dec 1, 2022, 5:45 PM | _ | Backend,Research | High | Done | Zivile Nebutovaite | Done | Task | _ | 10h
10142 | Dominykas Švilpa | Create Tag,Email, Email Template Entity CRUD | Working on Prisma models and planning work for the upcomming week. | GRAF-26 | _ | _ | graffinity | Oct 26, 2022, 2:20 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10131 | Kernius Survila | Set up Swagger | *Swagger integration * DB seeding w/ faker *ci fix *structure improvements | GRAF-25 | _ | _ | graffinity | Oct 20, 2022, 11:00 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10154 | Kernius Survila | Create Graffiti CRUD (update) | graffiti be update + preperation | GRAF-24 | _ | _ | graffinity | Nov 1, 2022, 8:07 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 30m
10140 | Morta Marija Matelyte | Create/Update Comment Functionality | Created comment model and CRUD in GRAF-23 branch. | GRAF-23 | GRAF-42 | GRAF-42 | graffinity | Oct 29, 2022, 6:00 PM | Morta Marija Matelyte | Backend | High | Done | Kernius Survila | Done | Task | _ | 1h 30m
10157 | Morta Marija Matelyte | Create/Update Comment Functionality | Research on Technical specification document, Updating comment entity functionality. | GRAF-23 | GRAF-42 | GRAF-42 | graffinity | Nov 3, 2022, 3:30 PM | Morta Marija Matelyte | Backend | High | Done | Kernius Survila | Done | Task | _ | 3h
10207 | Morta Marija Matelyte | Create/Update Comment Functionality | Fixed errors and checked if everything works with postman. | GRAF-23 | GRAF-42 | GRAF-42 | graffinity | Nov 17, 2022, 4:30 PM | Morta Marija Matelyte | Backend | High | Done | Kernius Survila | Done | Task | _ | 2h 30m
10209 | Morta Marija Matelyte | Create/Update Comment Functionality | Final updates on the comment functionality (added sorting by date), checked with Postman and opened a pull request. | GRAF-23 | GRAF-42 | GRAF-42 | graffinity | Nov 18, 2022, 1:30 PM | Morta Marija Matelyte | Backend | High | Done | Kernius Survila | Done | Task | _ | 2h
10147 | Morta Marija Matelyte | Create/Update Artist Functionality | Making updates to GRAF-22 and GRAF-23. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Oct 31, 2022, 3:00 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10159 | Morta Marija Matelyte | Create/Update Artist Functionality | Updating artist entity functionality. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 4, 2022, 5:00 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10168 | Morta Marija Matelyte | Create/Update Artist Functionality | Fixed errors, updated artist.service.ts and artist.controller.ts. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 7, 2022, 9:00 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10173 | Morta Marija Matelyte | Create/Update Artist Functionality | Made final edits to artist entity functionality and wrote down what tasks I’ve already finsihed and what I have left, considering task priorities. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 8, 2022, 11:00 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 45m
10188 | Morta Marija Matelyte | Create/Update Artist Functionality | Updated the ER model and created a pull request for GRAF-22. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 14, 2022, 6:30 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 1h 30m
10189 | Morta Marija Matelyte | Create/Update Artist Functionality | Tried checking if everything works with postman, found new errors, fixed a couple of them but not all. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 15, 2022, 10:30 AM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10190 | Morta Marija Matelyte | Create/Update Artist Functionality | Trying to fix errors. Figured out why it is happening, did not try to apply the solutions yet. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 15, 2022, 12:30 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10208 | Morta Marija Matelyte | Create/Update Artist Functionality | Finished all updates for Artist entity, checked with postman and created a pull request. | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 17, 2022, 7:30 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10211 | Morta Marija Matelyte | Create/Update Artist Functionality | Made changes based on comments on pull requests in the GRAF-22 and GRAF-23 branches | GRAF-22 | GRAF-42 | GRAF-42 | graffinity | Nov 21, 2022, 6:00 PM | Morta Marija Matelyte | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10178 | Dominykas Švilpa | Create/Update Tag Functionality | Updating the CRUD opartions ontag component | GRAF-21 | GRAF-42 | GRAF-42 | graffinity | Nov 3, 2022, 10:00 PM | Dominykas Švilpa | Backend | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10097 | Kernius Survila | Implement Nest.js instead of express.js |  | GRAF-20 | _ | _ | graffinity | Oct 10, 2022, 7:26 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10127 | Kernius Survila | Implement Nest.js instead of express.js |  | GRAF-20 | _ | _ | graffinity | Oct 19, 2022, 8:47 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 6h
10133 | Dominykas Švilpa | Structure update + Mapper + Auth + User entity | Writing Email and EmailTemplate entities | GRAF-19 | _ | _ | graffinity | Oct 23, 2022, 1:30 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10135 | Dominykas Švilpa | Structure update + Mapper + Auth + User entity | Fixing entities .spec files | GRAF-19 | _ | _ | graffinity | Oct 24, 2022, 8:30 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10148 | Kernius Survila | Structure update + Mapper + Auth + User entity | authorizaton & user be | GRAF-19 | _ | _ | graffinity | Oct 28, 2022, 8:52 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10059 | Kernius Survila | PSI Documentation writing (deadline: 2022-09-26) |  | GRAF-17 | _ | _ | graffinity | Sep 26, 2022, 11:00 AM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 1h 30m
10062 | Kernius Survila | PSI Documentation writing (deadline: 2022-09-26) |  | GRAF-17 | _ | _ | graffinity | Sep 25, 2022, 4:00 PM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 1h 30m
10067 | Dominykas Švilpa | PSI Documentation writing (deadline: 2022-09-26) | Finishing up team documentation and finalizing ideas and segments for the porject | GRAF-17 | _ | _ | graffinity | Sep 26, 2022, 12:00 AM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 3h
10071 | Zivile Nebutovaite | PSI Documentation writing (deadline: 2022-09-26) | Psi documentation initial writing | GRAF-17 | _ | _ | graffinity | Sep 25, 2022, 7:46 PM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 2h
10072 | Zivile Nebutovaite | PSI Documentation writing (deadline: 2022-09-26) | Group meeting Psi documentation writing | GRAF-17 | _ | _ | graffinity | Sep 26, 2022, 7:47 PM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 3h
10074 | Zivile Nebutovaite | PSI Documentation writing (deadline: 2022-09-26) |  | GRAF-17 | _ | _ | graffinity | Sep 26, 2022, 7:30 PM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 30m
10079 | Zivile Nebutovaite | PSI Documentation writing (deadline: 2022-09-26) |  | GRAF-17 | _ | _ | graffinity | Sep 27, 2022, 9:00 AM | _ | _ | High | Done | Kernius Survila | Done | Task | _ | 1h
10049 | Kernius Survila | Learning roadmap (preliminary) for Kernius | research, learning, looking for sources | GRAF-15 | _ | _ | graffinity | Sep 16, 2022, 5:26 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10056 | Morta Marija Matelyte | Learning roadmap (preliminary) for Morta | Cloned fronted and backend repositories, logged in to GitLab, read about git, github and JavaScript. | GRAF-14 | _ | _ | graffinity | Sep 23, 2022, 5:00 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 30m
10073 | Morta Marija Matelyte | Learning roadmap (preliminary) for Morta | Learning JavaScript, planning. | GRAF-14 | _ | _ | graffinity | Sep 26, 2022, 7:30 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 20m
10076 | Morta Marija Matelyte | Learning roadmap (preliminary) for Morta | JavaScript basics | GRAF-14 | _ | _ | graffinity | Sep 27, 2022, 12:00 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10077 | Morta Marija Matelyte | Learning roadmap (preliminary) for Morta | JavaScript, Typescript, HTTP, API’s, REST, CRUD, Node.js | GRAF-14 | _ | _ | graffinity | Sep 27, 2022, 4:00 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h 40m
10083 | Morta Marija Matelyte | Learning roadmap (preliminary) for Morta | Learning last things, starting backend work. | GRAF-14 | _ | _ | graffinity | Sep 28, 2022, 10:00 AM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 8h
10089 | Morta Marija Matelyte | Learning roadmap (preliminary) for Morta | Finishing last topics on the learning roadmap. | GRAF-14 | _ | _ | graffinity | Oct 5, 2022, 6:00 PM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 15m
10046 | Zivile Nebutovaite | Learning roadmap (preliminary) for Zivile | ts installation and learning | GRAF-13 | _ | _ | graffinity | Sep 21, 2022, 6:00 PM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10075 | Zivile Nebutovaite | Learning roadmap (preliminary) for Zivile | reading | GRAF-13 | _ | _ | graffinity | Sep 26, 2022, 9:00 PM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 30m
10080 | Zivile Nebutovaite | Learning roadmap (preliminary) for Zivile | learning | GRAF-13 | _ | _ | graffinity | Sep 27, 2022, 10:00 PM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10082 | Zivile Nebutovaite | Learning roadmap (preliminary) for Zivile | Workshop | GRAF-13 | _ | _ | graffinity | Sep 28, 2022, 11:30 AM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 8h
10130 | Zivile Nebutovaite | Learning roadmap (preliminary) for Zivile | no comment | GRAF-13 | _ | _ | graffinity | Oct 18, 2022, 4:30 PM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10045 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | installing and setting up TYPESCRIPT in wsl | GRAF-12 | _ | _ | graffinity | Sep 21, 2022, 7:00 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10064 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Learning javascript in freecodecamp.com | GRAF-12 | _ | _ | graffinity | Sep 23, 2022, 5:51 PM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10065 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Learning javascript in freecodecamp.com | GRAF-12 | _ | _ | graffinity | Sep 24, 2022, 1:30 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10084 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Setting up back-end of the project | GRAF-12 | _ | _ | graffinity | Sep 28, 2022, 7:39 PM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 8h
10115 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Learning and creating the first version of landing page header (navigation bar) | GRAF-12 | _ | _ | graffinity | Oct 8, 2022, 8:37 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10116 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Learning and creating the first version of landing page header (navigation bar) | GRAF-12 | _ | _ | graffinity | Oct 7, 2022, 8:38 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10118 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Working and learning about the back end of the project. | GRAF-12 | _ | _ | graffinity | Oct 11, 2022, 12:00 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10120 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Learning about the implementation of Google maps into the landing page (failing to implement miserably) | GRAF-12 | _ | _ | graffinity | Oct 14, 2022, 8:45 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10121 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | learning about JavaScript, Typescript, HTTP, API’s, REST, CRUD, Node.js to prepare for a workshop in wich we will be setting up the back end of the project | GRAF-12 | _ | _ | graffinity | Sep 27, 2022, 2:30 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10244 | Dominykas Švilpa | Learning roadmap (preliminary) for Dominykas | Team Building | GRAF-12 | _ | _ | graffinity | Dec 12, 2022, 6:23 PM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 11h
10048 | Kernius Survila | Set up frontend | git mirror | GRAF-11 | _ | _ | graffinity | Sep 16, 2022, 6:26 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10054 | Kernius Survila | Set up frontend | gitlab CI (external pull mirror), push mirror from github, set up, clean up | GRAF-11 | _ | _ | graffinity | Sep 22, 2022, 7:00 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10055 | Kernius Survila | Set up frontend | Gitlab CI runner containerizing, CI polishing | GRAF-11 | _ | _ | graffinity | Sep 23, 2022, 9:00 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10014 | Kernius Survila | Set up backend | backend project template | GRAF-10 | _ | _ | graffinity | Sep 13, 2022, 6:56 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 30m
10047 | Kernius Survila | Set up backend | git setup | GRAF-10 | _ | _ | graffinity | Sep 16, 2022, 6:25 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h
10106 | Kernius Survila | Set up backend | untracked hours | GRAF-10 | _ | _ | graffinity | Oct 10, 2022, 8:06 PM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 12h 30m
10124 | Dominykas Švilpa | Set up backend | Making some addiotional slides and altering other for the second presentation, dividing entities between members for next week’s work with Prisma. | GRAF-10 | _ | _ | graffinity | Oct 17, 2022, 8:37 AM | Kernius Survila | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10087 | Morta Marija Matelyte | Project Tasks | Preparing my part of the presentation. | GRAF-9 | _ | _ | graffinity | Oct 4, 2022, 8:00 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 30m
10088 | Morta Marija Matelyte | Project Tasks | Preparing slides and speech for presentation. | GRAF-9 | _ | _ | graffinity | Oct 5, 2022, 4:30 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 30m
10105 | Kernius Survila | Project Tasks | untracked hours | GRAF-9 | _ | _ | graffinity | Oct 3, 2022, 8:05 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 17h 30m
10117 | Dominykas Švilpa | Project Tasks | Researching and writting the report for the first presantation | GRAF-9 | _ | _ | graffinity | Oct 5, 2022, 8:39 AM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 6h
10119 | Dominykas Švilpa | Project Tasks | Writing the system non functiional requiroments part for the first report draft and making a slides to accomidate. | GRAF-9 | _ | _ | graffinity | Oct 12, 2022, 8:43 AM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 7h
10125 | Dominykas Švilpa | Project Tasks | Changing the header (navigation bar) of the landing page to fit the projects requiroments.(and failing miserably) | GRAF-9 | _ | _ | graffinity | Oct 17, 2022, 4:00 AM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10132 | Dominykas Švilpa | Project Tasks | Implementing the map into kthe landing page of the project and making some changes to fit multiple screensizes | GRAF-9 | _ | _ | graffinity | Oct 18, 2022, 6:32 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10180 | Dominykas Švilpa | Project Tasks | Writting “technologies we use” part on technical specifications for PSI | GRAF-9 | _ | _ | graffinity | Nov 6, 2022, 12:00 AM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10183 | Dominykas Švilpa | Project Tasks | Writting project tasks | GRAF-9 | _ | _ | graffinity | Nov 8, 2022, 2:28 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10239 | Dominykas Švilpa | Project Tasks | Discussing our plans | GRAF-9 | _ | _ | graffinity | Nov 22, 2022, 6:08 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10242 | Dominykas Švilpa | Project Tasks | working on project slides | GRAF-9 | _ | _ | graffinity | Nov 30, 2022, 6:19 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10243 | Dominykas Švilpa | Project Tasks | 24 hr task | GRAF-9 | _ | _ | graffinity | Dec 8, 2022, 6:20 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 9h
10246 | Dominykas Švilpa | Project Tasks | creating slides | GRAF-9 | _ | _ | graffinity | Dec 14, 2022, 4:00 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 5h
10257 | Morta Marija Matelyte | Project Tasks | Editing Requirements specification and Technical specification. | GRAF-9 | _ | _ | graffinity | Dec 16, 2022, 11:16 PM | _ | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h 30m
10007 | Dominykas Švilpa | Set-up tasks for Dominykas | researching implementation of google maps in a website | GRAF-7 | _ | _ | graffinity | Sep 12, 2022, 8:30 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 9m
10020 | Dominykas Švilpa | Set-up tasks for Dominykas | researching tools that would be used to implement google maps into a website | GRAF-7 | _ | _ | graffinity | Sep 13, 2022, 8:39 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 1h 30m
10038 | Dominykas Švilpa | Set-up tasks for Dominykas | Downloading wsl and learning basic commands that are used with git | GRAF-7 | _ | _ | graffinity | Sep 15, 2022, 12:00 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10039 | Dominykas Švilpa | Set-up tasks for Dominykas | Trying out and learning on front-end libraries on freecodecamp.com | GRAF-7 | _ | _ | graffinity | Sep 15, 2022, 9:00 PM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10040 | Dominykas Švilpa | Set-up tasks for Dominykas | Trying out and learning on front-end libraries on freecodecamp.com | GRAF-7 | _ | _ | graffinity | Sep 16, 2022, 4:00 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 3h
10041 | Dominykas Švilpa | Set-up tasks for Dominykas | Trying out and learning on front-end libraries on freecodecamp.com | GRAF-7 | _ | _ | graffinity | Sep 18, 2022, 1:00 PM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10043 | Dominykas Švilpa | Set-up tasks for Dominykas | finished trying out and the basics of Bootstrap jQuery and reactive on freecodecamp.com | GRAF-7 | _ | _ | graffinity | Sep 20, 2022, 1:30 AM | Dominykas Švilpa | _ | Medium | Done | Kernius Survila | Done | Task | _ | 4h
10193 | Zivile Nebutovaite | Set-up tasks for Zivile | Slide prep | GRAF-6 | _ | _ | graffinity | Nov 15, 2022, 7:22 PM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10222 | Zivile Nebutovaite | Set-up tasks for Zivile | Working on presentation slides | GRAF-6 | _ | _ | graffinity | Nov 30, 2022, 8:10 PM | Zivile Nebutovaite | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10015 | Morta Marija Matelyte | Set-up tasks for Morta | Set-up tasks | GRAF-5 | _ | _ | graffinity | Sep 13, 2022, 6:00 AM | Morta Marija Matelyte | _ | Medium | Done | Kernius Survila | Done | Task | _ | 2h
10003 | Zivile Nebutovaite | Code review log | Group chat Trying to choose a programing language, dbms. | GRAF-4 | _ | _ | graffinity | Sep 8, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10004 | Zivile Nebutovaite | Code review log | Group meeting | GRAF-4 | _ | _ | graffinity | Sep 9, 2022, 3:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10005 | Zivile Nebutovaite | Code review log | Group meeting 2 | GRAF-4 | _ | _ | graffinity | Sep 12, 2022, 7:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10023 | Zivile Nebutovaite | Code review log | Trying to fill out document questions Youtube videos about web dev | GRAF-4 | _ | _ | graffinity | Sep 11, 2022, 6:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 15m
10024 | Zivile Nebutovaite | Code review log | getting more familiar with confluence and jira | GRAF-4 | _ | _ | graffinity | Sep 13, 2022, 6:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 35m
10025 | Zivile Nebutovaite | Code review log | downloading vs code | GRAF-4 | _ | _ | graffinity | Sep 13, 2022, 7:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 25m
10026 | Zivile Nebutovaite | Code review log | Group meeting for document submission | GRAF-4 | _ | _ | graffinity | Sep 14, 2022, 6:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10028 | Zivile Nebutovaite | Code review log | Live Group meeting Setting up WSL | GRAF-4 | _ | _ | graffinity | Sep 15, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10029 | Zivile Nebutovaite | Code review log | Trying to fix problems with WSL | GRAF-4 | _ | _ | graffinity | Sep 15, 2022, 6:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10034 | Zivile Nebutovaite | Code review log | Group meeting Making a contract | GRAF-4 | _ | _ | graffinity | Sep 19, 2022, 11:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10035 | Zivile Nebutovaite | Code review log | Asking help from kernius with wsl | GRAF-4 | _ | _ | graffinity | Sep 19, 2022, 7:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 15m
10069 | Zivile Nebutovaite | Code review log | Group meeting | GRAF-4 | _ | _ | graffinity | Sep 22, 2022, 12:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10070 | Zivile Nebutovaite | Code review log | Group meeting | GRAF-4 | _ | _ | graffinity | Sep 25, 2022, 7:45 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10086 | Zivile Nebutovaite | Code review log | Group meeting | GRAF-4 | _ | _ | graffinity | Oct 4, 2022, 11:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10101 | Zivile Nebutovaite | Code review log | Group meeting | GRAF-4 | _ | _ | graffinity | Oct 11, 2022, 10:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10158 | Zivile Nebutovaite | Code review log | group meet | GRAF-4 | _ | _ | graffinity | Nov 1, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 6h
10160 | Zivile Nebutovaite | Code review log | reaserching and preparing diagrams for technical spesification | GRAF-4 | _ | _ | graffinity | Nov 5, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 6h
10161 | Zivile Nebutovaite | Code review log | reaserching and preparing diagrams for technical spesification | GRAF-4 | _ | _ | graffinity | Nov 4, 2022, 9:45 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10163 | Zivile Nebutovaite | Code review log | reasearch about technical specification | GRAF-4 | _ | _ | graffinity | Nov 2, 2022, 5:18 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10174 | Zivile Nebutovaite | Code review log | Group meet | GRAF-4 | _ | _ | graffinity | Nov 11, 2022, 11:55 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10186 | Zivile Nebutovaite | Code review log | Group meet for teem building | GRAF-4 | _ | _ | graffinity | Dec 12, 2022, 11:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 11h
10192 | Zivile Nebutovaite | Code review log | Team meeting | GRAF-4 | _ | _ | graffinity | Nov 14, 2022, 7:22 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10194 | Zivile Nebutovaite | Code review log | Slide prep | GRAF-4 | _ | _ | graffinity | Nov 16, 2022, 7:23 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10195 | Zivile Nebutovaite | Code review log | Slide prep | GRAF-4 | _ | _ | graffinity | Nov 14, 2022, 7:26 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10220 | Zivile Nebutovaite | Code review log | Group meet | GRAF-4 | _ | _ | graffinity | Nov 29, 2022, 8:08 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10223 | Zivile Nebutovaite | Code review log | group meet | GRAF-4 | _ | _ | graffinity | Nov 22, 2022, 8:11 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10009 | Morta Marija Matelyte | Research & Analysis log | Answering questions on project vision and preliminary analysis. | GRAF-3 | _ | _ | graffinity | Sep 9, 2022, 4:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10010 | Morta Marija Matelyte | Research & Analysis log | Finishing up answering questions for project vision and preliminary analysis. | GRAF-3 | _ | _ | graffinity | Sep 12, 2022, 3:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 20m
10011 | Morta Marija Matelyte | Research & Analysis log | Configured VS code for typescript. | GRAF-3 | _ | _ | graffinity | Sep 9, 2022, 9:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10013 | Morta Marija Matelyte | Research & Analysis log | Learning typescript basics | GRAF-3 | _ | _ | graffinity | Sep 13, 2022, 5:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 20m
10018 | Kernius Survila | Research & Analysis log | documents | GRAF-3 | _ | _ | graffinity | Sep 12, 2022, 7:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h 30m
10019 | Kernius Survila | Research & Analysis log | research + analysis | GRAF-3 | _ | _ | graffinity | Sep 13, 2022, 8:37 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10027 | Morta Marija Matelyte | Research & Analysis log | Research on group contract | GRAF-3 | _ | _ | graffinity | Sep 14, 2022, 9:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 20m
10031 | Morta Marija Matelyte | Research & Analysis log | Practice with Typescript | GRAF-3 | _ | _ | graffinity | Sep 18, 2022, 6:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10037 | Kernius Survila | Research & Analysis log | prisma, resources | GRAF-3 | _ | _ | graffinity | Sep 19, 2022, 4:49 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10042 | Morta Marija Matelyte | Research & Analysis log | Learning Typescript. | GRAF-3 | _ | _ | graffinity | Sep 19, 2022, 6:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10050 | Kernius Survila | Research & Analysis log | prisma, learning, other tools | GRAF-3 | _ | _ | graffinity | Sep 19, 2022, 5:56 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10051 | Kernius Survila | Research & Analysis log | seting up | GRAF-3 | _ | _ | graffinity | Sep 15, 2022, 7:28 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10053 | Morta Marija Matelyte | Research & Analysis log | Learning Typescript. | GRAF-3 | _ | _ | graffinity | Sep 20, 2022, 8:33 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10058 | Morta Marija Matelyte | Research & Analysis log | Writing general description for requirements specification. | GRAF-3 | _ | _ | graffinity | Sep 25, 2022, 3:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10078 | Morta Marija Matelyte | Research & Analysis log | Editing requerements specification, making a webpage mockup. | GRAF-3 | _ | _ | graffinity | Sep 27, 2022, 7:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10091 | Morta Marija Matelyte | Research & Analysis log | Rehearsing speech for presentation. | GRAF-3 | _ | _ | graffinity | Oct 5, 2022, 9:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10092 | Morta Marija Matelyte | Research & Analysis log | Researching user flow diagrams and ER models for our project. | GRAF-3 | _ | _ | graffinity | Oct 6, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10093 | Morta Marija Matelyte | Research & Analysis log | Making a log in flowchart. | GRAF-3 | _ | _ | graffinity | Oct 6, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10094 | Morta Marija Matelyte | Research & Analysis log | Making an ER model. | GRAF-3 | _ | _ | graffinity | Oct 6, 2022, 4:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10098 | Morta Marija Matelyte | Research & Analysis log | Research on project architecture | GRAF-3 | _ | _ | graffinity | Oct 10, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10099 | Morta Marija Matelyte | Research & Analysis log | Continuing making an ER model. | GRAF-3 | _ | _ | graffinity | Oct 10, 2022, 9:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10100 | Morta Marija Matelyte | Research & Analysis log | Researching all topics for the first draft of project report. | GRAF-3 | _ | _ | graffinity | Oct 10, 2022, 10:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10103 | Morta Marija Matelyte | Research & Analysis log | Improving the ER model | GRAF-3 | _ | _ | graffinity | Oct 11, 2022, 9:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10104 | Morta Marija Matelyte | Research & Analysis log | Writing the system architecture part for the first report draft and making a system architecture diagram. | GRAF-3 | _ | _ | graffinity | Oct 12, 2022, 3:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10107 | Zivile Nebutovaite | Research & Analysis log | Writing the preliminary design part for the first report draft. | GRAF-3 | _ | _ | graffinity | Oct 12, 2022, 3:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10108 | Zivile Nebutovaite | Research & Analysis log | Reasearch for projecyt report draft | GRAF-3 | _ | _ | graffinity | Oct 10, 2022, 4:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10109 | Zivile Nebutovaite | Research & Analysis log | Presentation preperation | GRAF-3 | _ | _ | graffinity | Oct 5, 2022, 5:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10110 | Zivile Nebutovaite | Research & Analysis log | Presentation preperation | GRAF-3 | _ | _ | graffinity | Oct 6, 2022, 6:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10111 | Zivile Nebutovaite | Research & Analysis log | Learning about prisma | GRAF-3 | _ | _ | graffinity | Oct 9, 2022, 12:26 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10112 | Zivile Nebutovaite | Research & Analysis log | Reasearch about preliminary design | GRAF-3 | _ | _ | graffinity | Oct 10, 2022, 7:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10113 | Dominykas Švilpa | Research & Analysis log | Researching all topics for the first draft of project report. | GRAF-3 | _ | _ | graffinity | Oct 3, 2022, 8:35 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10114 | Dominykas Švilpa | Research & Analysis log | Writing the system non-functional requiroments part for the first report draft | GRAF-3 | _ | _ | graffinity | Oct 4, 2022, 8:35 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10122 | Morta Marija Matelyte | Research & Analysis log | Logging all meeting notes on confluence that were not there. | GRAF-3 | _ | _ | graffinity | Oct 17, 2022, 9:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 45m
10126 | Morta Marija Matelyte | Research & Analysis log | Redid the Use Case diagram and ER model because I found a couple mistakes. | GRAF-3 | _ | _ | graffinity | Oct 18, 2022, 10:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 45m
10128 | Kernius Survila | Research & Analysis log | nu visko buvo, uzmirsau +- tiek uztimint | GRAF-3 | _ | _ | graffinity | Oct 18, 2022, 6:48 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 20h
10129 | Zivile Nebutovaite | Research & Analysis log | Group meet doing slides | GRAF-3 | _ | _ | graffinity | Oct 17, 2022, 2:49 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10134 | Morta Marija Matelyte | Research & Analysis log | Working with Prisma and trying to fix some errors. | GRAF-3 | _ | _ | graffinity | Oct 23, 2022, 5:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10136 | Morta Marija Matelyte | Research & Analysis log | Tried fixing some errors with wsl. | GRAF-3 | _ | _ | graffinity | Oct 24, 2022, 7:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h 30m
10137 | Morta Marija Matelyte | Research & Analysis log | Trying to fix errors on wsl, reinstalling wsl and some packages, creating artist, comment models on Prisma with their relationships. | GRAF-3 | _ | _ | graffinity | Oct 25, 2022, 6:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10152 | Morta Marija Matelyte | Research & Analysis log | Reviewing branch GRAF-19 to see what changes have been made. | GRAF-3 | _ | _ | graffinity | Nov 1, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10156 | Morta Marija Matelyte | Research & Analysis log | Researching how to write technical specification for PSI. | GRAF-3 | _ | _ | graffinity | Nov 2, 2022, 8:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10164 | Morta Marija Matelyte | Research & Analysis log | Researching structural aspects for PSI documentation and trying to fix an error in the artist entity functionality code (GRAF-22). | GRAF-3 | _ | _ | graffinity | Nov 6, 2022, 5:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 45m
10165 | Morta Marija Matelyte | Research & Analysis log | Making a frontend structure diagram for technical specification. | GRAF-3 | _ | _ | graffinity | Nov 7, 2022, 9:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10166 | Morta Marija Matelyte | Research & Analysis log | Writing the frontend structural aspects part of the technical specification (for SE). | GRAF-3 | _ | _ | graffinity | Nov 7, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h 30m
10167 | Morta Marija Matelyte | Research & Analysis log | Making the sturctural backend aspect diagram. | GRAF-3 | _ | _ | graffinity | Nov 7, 2022, 6:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10169 | Zivile Nebutovaite | Research & Analysis log | psi | GRAF-3 | _ | _ | graffinity | Nov 7, 2022, 8:34 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10170 | Morta Marija Matelyte | Research & Analysis log | Researching how to fix some mistakes in the technical specification (for SE) | GRAF-3 | _ | _ | graffinity | Nov 8, 2022, 3:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10171 | Zivile Nebutovaite | Research & Analysis log | psi | GRAF-3 | _ | _ | graffinity | Nov 8, 2022, 6:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10191 | Morta Marija Matelyte | Research & Analysis log | Updated the ER model, submitted it to teammates for review, redid the Use Case Diagram, prepared some questions for reviewing tomorrow. | GRAF-3 | _ | _ | graffinity | Nov 16, 2022, 3:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10216 | Morta Marija Matelyte | Research & Analysis log | Research. | GRAF-3 | _ | _ | graffinity | Nov 22, 2022, 6:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10219 | Morta Marija Matelyte | Research & Analysis log | Research and planning personal work. | GRAF-3 | _ | _ | graffinity | Nov 29, 2022, 7:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10233 | Kernius Survila | Research & Analysis log | something something | GRAF-3 | _ | _ | graffinity | Nov 30, 2022, 8:42 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10234 | Morta Marija Matelyte | Research & Analysis log | Taking a walk to take pictures of graffiti near me, making slides, preparing everything for my presentation. | GRAF-3 | _ | _ | graffinity | Nov 30, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10235 | Morta Marija Matelyte | Research & Analysis log | Preparing for the presentation. | GRAF-3 | _ | _ | graffinity | Nov 30, 2022, 9:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10237 | Dominykas Švilpa | Research & Analysis log | Reserching about alghorithms | GRAF-3 | _ | _ | graffinity | Nov 20, 2022, 6:06 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10238 | Dominykas Švilpa | Research & Analysis log | Reserching algorithms | GRAF-3 | _ | _ | graffinity | Nov 21, 2022, 8:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10241 | Dominykas Švilpa | Research & Analysis log | Merged a new pull request, talked about algorithms (how and where we will implement them). Worked on slides for the next presentation (workload division and making actual changes). | GRAF-3 | _ | _ | graffinity | Nov 29, 2022, 6:13 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10245 | Zivile Nebutovaite | Research & Analysis log | Group meet working on 24h task | GRAF-3 | _ | _ | graffinity | Dec 8, 2022, 6:29 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10249 | Kernius Survila | Research & Analysis log | 24 hour task, documentation and things like that | GRAF-3 | _ | _ | graffinity | Dec 7, 2022, 5:45 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 17h
10251 | Kernius Survila | Research & Analysis log | everything I didnt account for | GRAF-3 | _ | _ | graffinity | Dec 16, 2022, 5:46 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 9h
10252 | Kernius Survila | Research & Analysis log | *research *implementation *planning *various documentation *stressing ab stuff | GRAF-3 | _ | _ | graffinity | Dec 2, 2022, 5:48 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 9h
10001 | Kernius Survila | Meetings log | meeting about technical specification | GRAF-2 | _ | _ | graffinity | Sep 12, 2022, 7:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10006 | Kernius Survila | Meetings log | Introduction meeting | GRAF-2 | _ | _ | graffinity | Sep 9, 2022, 3:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10008 | Morta Marija Matelyte | Meetings log | Introductory meeting | GRAF-2 | _ | _ | graffinity | Sep 9, 2022, 3:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10012 | Morta Marija Matelyte | Meetings log | Sharing answers about project vision and preliminary analysis, discussing future plans. | GRAF-2 | _ | _ | graffinity | Sep 12, 2022, 7:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10016 | Morta Marija Matelyte | Meetings log | Final meeting before first document submission. | GRAF-2 | _ | _ | graffinity | Sep 14, 2022, 6:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10017 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Sep 14, 2022, 8:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10021 | Dominykas Švilpa | Meetings log | team meeting | GRAF-2 | _ | _ | graffinity | Sep 9, 2022, 3:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10022 | Dominykas Švilpa | Meetings log | team meeting | GRAF-2 | _ | _ | graffinity | Sep 12, 2022, 7:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 45m
10030 | Morta Marija Matelyte | Meetings log | Final set-up process, learning how to use git and github. | GRAF-2 | _ | _ | graffinity | Sep 15, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10032 | Kernius Survila | Meetings log | contract meeting | GRAF-2 | _ | _ | graffinity | Sep 19, 2022, 11:21 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10033 | Morta Marija Matelyte | Meetings log | Editing group contract. | GRAF-2 | _ | _ | graffinity | Sep 19, 2022, 11:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10036 | Kernius Survila | Meetings log | in person meeting, git | GRAF-2 | _ | _ | graffinity | Sep 15, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10044 | Dominykas Švilpa | Meetings log | Reviewing out team contract | GRAF-2 | _ | _ | graffinity | Sep 19, 2022, 12:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10052 | Kernius Survila | Meetings log | meeting | GRAF-2 | _ | _ | graffinity | Sep 19, 2022, 7:29 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10057 | Morta Marija Matelyte | Meetings log | Dividing workload for writing requirements specification. | GRAF-2 | _ | _ | graffinity | Sep 25, 2022, 12:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 30m
10060 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Sep 26, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10061 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Sep 22, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10063 | Dominykas Švilpa | Meetings log |  | GRAF-2 | _ | _ | graffinity | Sep 22, 2022, 12:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10068 | Morta Marija Matelyte | Meetings log | Writing requirements specification, deciding on exact features our webage will have. | GRAF-2 | _ | _ | graffinity | Sep 26, 2022, 11:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10081 | Morta Marija Matelyte | Meetings log | Final edits on requirements specification. | GRAF-2 | _ | _ | graffinity | Sep 27, 2022, 9:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10085 | Morta Marija Matelyte | Meetings log | Preparing for the first presentation. | GRAF-2 | _ | _ | graffinity | Oct 4, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10090 | Morta Marija Matelyte | Meetings log | Finishing up our first presentation slides. | GRAF-2 | _ | _ | graffinity | Oct 5, 2022, 8:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10095 | Kernius Survila | Meetings log | workshop | GRAF-2 | _ | _ | graffinity | Sep 28, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10096 | Kernius Survila | Meetings log | workshop | GRAF-2 | _ | _ | graffinity | Sep 28, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10102 | Morta Marija Matelyte | Meetings log | Editing ER model, finalizing division for writing first report draft, working on back end. | GRAF-2 | _ | _ | graffinity | Oct 11, 2022, 10:30 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10123 | Morta Marija Matelyte | Meetings log | Making slides for the second presentation, dividing entities between members for next week’s work with Prisma. | GRAF-2 | _ | _ | graffinity | Oct 17, 2022, 12:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10141 | Morta Marija Matelyte | Meetings log | Working on Prisma models and planning work for the upcomming week. | GRAF-2 | _ | _ | graffinity | Oct 26, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10151 | Morta Marija Matelyte | Meetings log | Merging branches, overviewing what each teammember worked on, planning tasks for the upcomming week. | GRAF-2 | _ | _ | graffinity | Nov 1, 2022, 2:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 6h
10153 | Kernius Survila | Meetings log | workshop | GRAF-2 | _ | _ | graffinity | Nov 1, 2022, 8:07 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 6h
10172 | Morta Marija Matelyte | Meetings log | Making final edits on our technical specification (for SE). | GRAF-2 | _ | _ | graffinity | Nov 8, 2022, 8:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 2h
10175 | Dominykas Švilpa | Meetings log | Workshop | GRAF-2 | _ | _ | graffinity | Nov 1, 2022, 2:19 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 6h
10185 | Morta Marija Matelyte | Meetings log | Planning | GRAF-2 | _ | _ | graffinity | Nov 11, 2022, 9:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10187 | Morta Marija Matelyte | Meetings log | Planning workload for each member for the upcomming week. Includes slides for the next assigment, work from before that needs to be finished and research for upcommong tasks. | GRAF-2 | _ | _ | graffinity | Nov 14, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10196 | Dominykas Švilpa | Meetings log | Planning workload for each member for the upcomming week. Includes slides for the next assigment, work from before that needs to be finished and research for upcommong tasks. | GRAF-2 | _ | _ | graffinity | Nov 14, 2022, 12:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10199 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 14, 2022, 7:42 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10200 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 15, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10201 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 16, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10202 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 17, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10203 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 12, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10204 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 11, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10205 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Nov 10, 2022, 7:44 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h 30m
10206 | Kernius Survila | Meetings log | unlogged hours | GRAF-2 | _ | _ | graffinity | Nov 9, 2022, 7:44 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10213 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Nov 22, 2022, 12:07 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10214 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Nov 22, 2022, 12:07 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 4h
10215 | Morta Marija Matelyte | Meetings log | Discussed plans for the next week. | GRAF-2 | _ | _ | graffinity | Nov 22, 2022, 12:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10218 | Morta Marija Matelyte | Meetings log | Merged a new pull request, talked about algorithms (how and where we will implement them). Worked on slides for the next presentation (workload division and making actual changes). | GRAF-2 | _ | _ | graffinity | Nov 29, 2022, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10226 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Nov 29, 2022, 8:40 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10231 | Kernius Survila | Meetings log |  | GRAF-2 | _ | _ | graffinity | Nov 23, 2022, 8:41 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 6h
10236 | Morta Marija Matelyte | Meetings log | 24 hour task. | GRAF-2 | _ | _ | graffinity | Dec 8, 2022, 1:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 10h
10248 | Kernius Survila | Meetings log | kazkas panasaus | GRAF-2 | _ | _ | graffinity | Dec 6, 2022, 5:45 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 9h
10250 | Kernius Survila | Meetings log | buvo | GRAF-2 | _ | _ | graffinity | Dec 15, 2022, 5:46 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10254 | Morta Marija Matelyte | Meetings log | Preparing slides for the last presentation, making future plans. | GRAF-2 | _ | _ | graffinity | Dec 13, 2022, 3:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10255 | Morta Marija Matelyte | Meetings log | Preparing for PSI presentation, making plans for the upcomming week. | GRAF-2 | _ | _ | graffinity | Dec 16, 2022, 1:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h 30m
10256 | Morta Marija Matelyte | Meetings log | Reviewing new information. | GRAF-2 | _ | _ | graffinity | Dec 16, 2022, 7:00 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 1h
10259 | Morta Marija Matelyte | Meetings log | Made meetings plans for the upcomming 2 weeks, wrote down tasks, prioritised, them, started working separately on appointed tasks. | GRAF-2 | _ | _ | graffinity | Dec 28, 2022, 6:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10261 | Morta Marija Matelyte | Meetings log | Planning, worked on our own tasks. | GRAF-2 | _ | _ | graffinity | Jan 2, 2023, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10262 | Morta Marija Matelyte | Meetings log | Working on our own tasks together. | GRAF-2 | _ | _ | graffinity | Jan 5, 2023, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10263 | Morta Marija Matelyte | Meetings log | Working on our own tasks. | GRAF-2 | _ | _ | graffinity | Jan 6, 2023, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10264 | Morta Marija Matelyte | Meetings log | Working on the report. | GRAF-2 | _ | _ | graffinity | Jan 10, 2023, 4:30 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10267 | Morta Marija Matelyte | Meetings log | Working on the report and testing, other divided tasks. | GRAF-2 | _ | _ | graffinity | Jan 11, 2023, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 12h
10268 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Jan 11, 2023, 7:41 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 12h
10269 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Jan 10, 2023, 7:41 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10270 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Jan 6, 2023, 7:42 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 7h
10271 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Jan 5, 2023, 7:42 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10272 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Jan 2, 2023, 7:42 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10273 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Dec 28, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10274 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Dec 19, 2022, 7:43 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 8h
10275 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Dec 16, 2022, 7:44 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 3h
10276 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Dec 13, 2022, 7:44 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 5h
10277 | Zivile Nebutovaite | Meetings log |  | GRAF-2 | _ | _ | graffinity | Jan 12, 2023, 7:46 PM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 12h
10278 | Morta Marija Matelyte | Meetings log | Final changes to the project, finishinh the report, submitting the project. | GRAF-2 | _ | _ | graffinity | Jan 12, 2023, 11:00 AM | _ | _ | Lowest | _ | Kernius Survila | Other | Story | _ | 12h
| _ |  | _ | _ | _ | _ | _ |  | _ | _ | _ | _ | _ | _ | _ | _ | 994h 30m